## 1. Product Overview
Item | Description
Product Name | ClauseIQ
Product Vision/ Purpose | "Every Clause decoded, Every Risk quatified"
Business Goals / Key Success factors | Empowerment, Literacy, Monetization, Integrity, Frictionless Experience
Primary Stakeholders | Freelancers, Interns, Employees

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
| Major features | Mandatory | Mandatory |  |  | (optional) | Mandatory | Mandatory | Mandatory | Mandatory
E1 | Cloud LLM Mode Integration | US1 | The current webLLM models is slower and less powerful, so in the next tier we're are allowing for the use of cloud based LLM's such as gemini, claude etc via api's . This integration has to be done into the current project. | API Integration(BYOK/Premium) | Must Have | 13 | Done | Dev Team(Whole Team) | Done
|  |  |  | Fine tuning the LLM(system instruction) | Must Have | 13 |  | Gagan
|  |  |  | PII Data Masking | Must Have | 13
|  |  |  | Setting Guardrails | Must Have | 13
|  |  |  | Data Demasking for personalization | Must Have | 13
|  |  |  | Ensuring Avaliability 24/7 | Must Have | 13
E2 | Localization | US2 | Jurisdiction-Aware Auditing: ClauseIQ identifies if your contract complies with local laws, ensuring your rights are protected wherever you work | A Rag containing legal labour laws from major countries based on demand | Must Have | 13 | Done | Dev Team | Done
|  |  |  | Store the Rag in a vector database | Must Have | 13 |  | David & Gagan
|  |  |  | Add countries data based on request or demand | Must Have | 13
|  |  |  | Accurately classify the contract based on jurisdiction | Must Have | 13
E3 | Database Functionality | US3 | Store each User profile and enable the user to securely store the analysis made from their entered contract | User Authentication | Must Have | 8 | Done | Dev Team(Backend Team) | Done
|  |  |  | User Profile | Must Have | 8 |  | Gagan
|  |  |  | User History(i.e their prev contracts) | Must Have | 8
E4 | Mulit-lingual Support | US4 | Allow contracts in other languages to be analyzed and responses or the result to be given in other languages as well | Localization | Should Have | 8 | In Progress | Dev Team(Frontend Team) | Yet To be Done
|  |  |  | Translation | Should Have | 8 |  | Dhruv Sharma
E5 | Privacy | US5 | Masking and demasking of PII | Regex Patterns | Must Have | 13 | Done | Dev Team | Done
Deepak & Revanth
Notes: | MoSCoW
|  | Must Have | Critical requirements that are essential for the project's success and must be delivered.
|  | Should Have | Important requirements that are highly desirable but not vital; the project can still be delivered without them, but it would be less ideal.
|  | Could Have | "Nice-to-have" requirements that are less important and have a lower impact if they are not included.
|  | Won't Have | Requirements that are not being delivered in the current project or timeframe, but may be considered for future iterations.
Story Points
|  | Fibonacci | 0,1,1,2,3,5,8,13,21,34,….
|  | (Modified) | 0,1,1,2,3,5,8,13,20 (points decided based on a User Story's complexity, effort needed & riks)
Ends at 20. Rarely extended to 40 and 100 for very large tasks.

## 3. Roadmap
Release |  | Key Features | Dependencies | Demo Status
Llist Epic Names
v0.1 | 2026-04-12 | Basic MVP with 21-heuristic Extraction | WEBLLM, REGEX | Done
v0.2 | 2026-04-19 | Cloud Based LLM Integration | Requires API upgrade & integration along with Data Masking | Done
v0.3 | 2026-04-24 | Database Functionality & Localization | Serveless database integration(Convex) and jusridictional support | Done
v0.4 | 2026-05-02 | Mulit-lingual support needed to be added | Requires API integration | Planned
v1.0 | 2026-05-03 | Final Product (Version 1.0) | All above mentioned features | Released

## 4. Retrospective
What Went Well | What Didn’t Go Well | Improvements / Action Items | Owner
Net time what will you do differently
Version v0.1
Team Collaboration was great | Focused too much on Privacy | Need to implement the entire system and include privacy as a particular feature | Team Lead
Version v1.0 | Balanced Features | Implemented | Team Lead